## Slide 1: Contract Closeout Module November 9, 2020

## Slide 2: Physically Completed
A contract is physically completed when the contractor has completed the required deliveries and the Government has inspected and accepted the supplies; or the contractor has performed all services and the Government has accepted these services, option provisions, if any, have expired; or the Government has given the contractor a notice of complete contract termination. (FAR 4.804-4)
Once a contract is physically completed, the administrative closeout can begin

## Slide 3: Administrative Closeout
Completing all tasks necessary and required to prepare the hard copy contract file for closeout and archiving and closing the electronic record which includes Prism and FPDS closure
All contracts must be closed out in a timely manner in accordance with FAR 4.804
Timely closeout will protect the Government’s interests and will allow for repurposing of residual funds before they expire

## Slide 4: Procedures for Closing Out Contract Files - FAR 4.804-5
Closeout procedures ensure:
(1) Disposition of classified materials
(2) Final patent report clearance
(3) Final royalty report clearance
(4) No Outstanding value engineering
(5) Plant clearance report
(6) Property clearance
(7) Interim or disallowed costs are settled
(8) Price revision is completed
(9) Subcontracts are settled by Prime
(10) Prior-year indirect cost rates settled
(11) Termination docket completed
(12) Contract audit completed
(13) Contractor’s closing statement submitted
(14) Contractor’s final invoice submitted
(15) Contract funds review completed and excess funds deobligated
(16) Contract Completion Statement

## Slide 5: Contract Closeout Timeframe After Physical Completion FAR 4.804-1
Contract files should not be closed if the contract is in litigation or under appeal, or if all termination actions have not been completed.
Files should be closed out as soon as they are eligible.
Type of Contract | Closeout Time Standard
Orders issued using Simplified Acquisition Procedures (SAP) | Within 60 days of physical completion
Firm-fixed-price contracts, other than those using simplified acquisition procedures | Within 6 months of physical completion
Contracts requiring settlement of indirect cost rates | Within 36 months of physical completion
All other contracts | Within 20 months of physical completion

## Slide 6: Four Administrative Closeout Scenarios for Prism and FPDS
Without Deobligation Modification and Without FPDS Reporting | With Deobligation Modification and Without FPDS Reporting
Without Deobligation Modification and With FPDS Reporting | With Deobligation Modification and With FPDS Reporting
System closure in PRISM and FPDS cannot occur until all procedures for closing out contract files have been completed.
System closure can be combined with a Deobligation of funds modification as explained in the following scenarios.

## Slide 7: Closeout without Deobligation Modification and without FPDS Reporting
  Step 1 – Confirm:
    There are no ($0.00) idle funds to be deobligated
    Award was not originally reported to FPDS
    Award has been fully received
    Award has been fully invoiced
    Award has been fully paid
  Step 2 – Conduct administrative closeout in PRISM:
    Select the last “RELEASED” document (Base or Modification)
    Navigate to Knowledge Article Performing Closeout for a Document in PRISM
    Perform the following process steps: 1 through 4, 20, 21, 22, and 23

## Slide 8: Closeout without Deobligation Modification and with FPDS Reporting
  Step 1 – Confirm:
  There are no ($0.00) idle funds to be deobligated
  Award was reported to FPDS
  Award has been fully received
  Award has been fully invoiced
  Award has been fully paid
  Step 2 – Prepare a modification to facilitate FPDS Reporting
  Annotate “Reason for Modification” as “K Close Out”
  Launch FPDS and report the modification
  Route the modification to approver
  Wait for modification to be approved
  NOTE: By choosing “Reason for Modification as “K Close Out” FPDS Record will automatically be updated (to a closed status) and no additional steps are required to complete FPDS Reporting
  Step 3 – Conduct administrative closeout in PRISM
  Select the last “RELEASED” modification to the award
  Navigate to Knowledge Article Performing Closeout for a Document in PRISM
  Perform the following process steps: 1 through 4, 20, 21, 22, and 23

## Slide 9: Closeout with Deobligation Modification and without FPDS Reporting
  Step 1 – Confirm:
  Total amount of idle funds to be deobligated
  Award was not originally reported to FPDS
  Award has been fully received
  Award has been fully invoiced
  Award has been fully paid WITH remaining idle funds that must be deobligated
  Step 2 – Prepare modification in PRISM to deobligate idle funds:
  Annotate “Reason for Modification” as “K Close Out”
  Route the modification to approver
  Wait for modification to be approved
  Step 3 – Conduct administrative closeout in PRISM:
  Select the last “RELEASED” Modification
  Navigate to the knowledge article: Performing Closeout for a Document in PRISM
  Perform the follow processes steps: 1 through 4, 20, 21, 22, and 23

## Slide 10: Closeout with Deobligation Modification and with FPDS Reporting
  Step 1 – Confirm:
  Total amount of idle funds to be deobligated
  Award was reported to FPDS
  Award has been fully received
  Award has been fully invoiced
  Award has been fully paid WITH remaining funds that must be deobligated
  Step 2 – Prepare modification in PRISM to deobligate idle funds
  Annotate “Reason for Modification” as “K Close Out”
  Launch FPDS and report the modification
  Route the modification to approver
  Wait for modification to be approved
  NOTE: By choosing “Reason for Modification as “K Close Out” FPDS Record will automatically be updated (to a closed status) and no additional steps are required to complete FPDS Reporting
  Step 3 – Conduct administrative closeout in PRISM
  Select the last RELEASED modification
  Navigate to the knowledge article: Performing Closeout for a Document in PRISM
  Perform the following process steps: 1 through 4, 20, 21, 22, and 23

## Slide 11: Warning!
The base award and all modifications, if any, MUST be in a “RELEASED” or “COMPLETED” status prior to performing PRISM closeout. Once an award is “CLOSED” in PRISM and in FPDS, it cannot be re-opened.
The PRISM Buyer, Contracting Officer, and Document Owner associated with an award can close a document in PRISM.

## Slide 12: Records Retention
On September 12, 2014, the retention period changed to six years after final payment.
All contract and purchase card files with a final payment date on or after September 12, 2011, must be retained for six years after the date of final payment. FAR 4.805

## Slide 13: Appendix 1 – PRISM Definition of Terms
“Released” This status describes orders (awards/documents) that have been approved and released. The order must be in the “Released” status to allow for receiving and/or invoice payment to occur.
  NOTE: In order for a document to be in a “Released” status, the approver approves the award in PRISM and when the award passes the financial validation, the order is then moved to a “Released” status.
“Closed” This status describes orders (awards/documents) that have been closed out. Further transactions cannot be initiated on closed documents.
  NOTE: Closing an award in PRISM is an administrative task. It will not result in financial transactions (i.e. funds being de-obligated). If necessary, a de-obligation modification must take place PRIOR to closing the award in PRISM. The end user cannot change the status based on the configurations established at NIH.